## Risk Register
Risk ID | Asset ID | Risk Description | Threat | Vulnerability | Impact (1-3) | Likelihood (1-3) | Risk Score | Risk Level | Business Impact | Mitigation Strategy | NIST Controls | Status | Risk Owner | Target Date
R-001 | AST-001 | Unauthorized Access to Active Directory | Credential compromise, insider threat, external attack | No MFA implemented, shared admin passwords, no PAM | 3 | 3 | 9 | High | Complete system compromise, unauthorized access to all resources | Implement MFA, deploy PAM solution, eliminate shared accounts | IA-2, IA-2(1), AC-2, AC-6 | Open | IT Manager | 2026-02-15
R-002 | AST-002, AST-003 | Data Breach / Data Loss | External attack, insider threat, ransomware | No DLP solution, no data classification, no encryption policy | 3 | 3 | 9 | High | Loss of sensitive data, regulatory fines, reputational damage | Implement DLP, classify data, deploy encryption, establish data governance | SC-28, MP-6, SC-13, SI-12 | Open | IT Manager | 2026-03-31
R-003 | AST-002, AST-005 | Undetected Cyber Attack | APT, malware, lateral movement, exfiltration | No SIEM, no centralized logging, no SOC, limited monitoring | 3 | 3 | 9 | High | Prolonged breach, extensive data loss, system compromise | Deploy SIEM, implement centralized logging, establish 24/7 monitoring | AU-2, AU-6, SI-4, IR-5 | Open | IT Manager | 2026-04-30
R-004 | AST-001 | Lack of Cybersecurity Governance | Strategic misalignment, compliance failures | No cybersecurity strategy, no information security policy, roles undefined | 2 | 3 | 6 | High | Regulatory non-compliance, ineffective security program, board liability | Develop cybersecurity strategy, create infosec policy, define roles and responsibilities | PL-1, PL-2, PL-8, PM-1 | Open | CISO / IT Manager | 2026-03-15
R-005 | AST-014 | Supply Chain Attack | Third-party compromise, vendor breach | No TPRM process, no vendor security assessments, no contract security clauses | 2 | 3 | 6 | High | Breach via trusted vendor, data exposure, service disruption | Establish TPRM program, conduct vendor assessments, update contracts | SR-2, SR-3, SA-9 | Open | Procurement Manager | 2026-06-30
R-006 | AST-001, AST-008 | Weak Remote Access Security | Compromised remote access, VPN exploitation | No MFA for VPN, contractor access not managed, no network access control | 3 | 2 | 6 | High | Unauthorized remote access, lateral movement from compromised accounts | Implement MFA for VPN, manage contractor access, deploy NAC | AC-17, IA-2(1), AC-20 | Open | Network Team Leader | 2026-03-31
R-007 | AST-006 | Vulnerability Exploitation | Exploit of known vulnerabilities, zero-day attacks | Ad-hoc vulnerability scanning, no formal VM program, high/severe vulns unresolved | 3 | 2 | 6 | High | System compromise, privilege escalation, data breach | Establish formal VM program, remediate critical vulns, regular scanning | RA-5, SI-2 | Open | IT Manager | 2026-02-28
R-008 | All Systems | Ineffective Incident Response | Delayed detection, inadequate containment | No incident response plan, no IR team, no runbooks, no 24/7 coverage | 2 | 3 | 6 | High | Extended dwell time, ineffective containment, regulatory reporting failures | Develop IR plan, establish IR team, create runbooks, conduct tabletop exercises | IR-1, IR-4, IR-8 | Open | IT Manager | 2026-04-15
R-009 | AST-002, AST-003 | Lack of Data Protection Controls | Unauthorized data access, data leakage | No data classification, USB drives allowed, no removable media policy | 2 | 2 | 4 | Medium | Sensitive data exfiltration, USB-based malware, intellectual property theft | Classify data, restrict USB usage, implement removable media controls | MP-3, MP-7, SC-28 | Open | IT Manager | 2026-05-31
R-010 | AST-010 | Configuration Drift | Unauthorized changes, misconfigurations | No change management process, no configuration baselines | 2 | 2 | 4 | Medium | System instability, security vulnerabilities, compliance failures | Implement change management, establish configuration baselines, automate compliance | CM-2, CM-3, CM-6 | Open | IT Manager | 2026-05-15
R-011 | AST-009 | Insufficient Security Awareness | Phishing attacks, social engineering | Basic training only, no phishing simulations, no ongoing awareness | 2 | 2 | 4 | Medium | Successful phishing, credential compromise, malware infection | Enhance training, conduct phishing simulations, quarterly awareness campaigns | AT-2, AT-3 | Open | HR Manager | 2026-03-31
R-012 | All Systems | Inadequate Audit Logging | Undetected malicious activity, no forensics | Logs not reviewed, no centralized logging, no retention policy | 2 | 2 | 4 | Medium | Inability to investigate incidents, compliance failures, no accountability | Centralize logging, implement log review process, define retention | AU-2, AU-3, AU-6, AU-12 | Open | IT Manager | 2026-04-30

## Legend
Risk Scoring Matrix
Formula: | Risk Score = Impact × Likelihood
Impact Scale | Rating | Description
High | 3 | Significant financial loss (>$500K), severe operational impact, major reputational damage
Medium | 2 | Moderate financial loss ($100K-$499K), moderate operational impact
Low | 1 | Minor financial loss (<$100K), minimal operational impact
Likelihood Scale | Rating | Description
Likely | 3 | Great chance of occurrence, already happened or happening
Moderate | 2 | Moderate chances of occurrence, may happen
Unlikely | 1 | Unlikely to happen, very rare occurrence
Risk Level | Risk Score | Meaning
Low | 1-3 | Acceptable risk, monitor
Medium | 4-5 | Needs mitigation or justification
High | 6-9 | Unacceptable, treatment required immediately