## Recommendations Roadmap
Rec ID | Risk ID | Recommendation | Description | NIST Controls | Priority | Timeline | Phase | Est. Cost (USD) | Owner | Status | Business Justification
REC-001 | R-001 | Deploy Multi-Factor Authentication (MFA) | Implement MFA for all users starting with privileged accounts, VPN, and cloud services (Azure AD, O365) | IA-2(1), AC-2 | Critical | 0-3 months | Phase 1: Quick Wins | 75000 | IT Manager | Not Started | Immediate risk reduction for credential compromise
REC-002 | R-004 | Develop Information Security Policy Framework | Create comprehensive information security policy, define cybersecurity strategy, establish governance structure | PL-1, PL-2, PL-8 | Critical | 0-3 months | Phase 1: Quick Wins | 50000 | CISO / IT Manager | Not Started | Foundation for entire security program
REC-003 | R-001 | Eliminate Shared Admin Accounts and Deploy PAM | Implement privileged access management solution, create individual admin accounts, establish privileged access reviews | AC-2, AC-6, IA-5 | Critical | 0-3 months | Phase 1: Quick Wins | 100000 | IT Manager | Not Started | Accountability and control over privileged access
REC-004 | R-007 | Establish Formal Vulnerability Management Program | Formalize Qualys usage, define scanning schedules, create remediation SLAs, prioritize critical vulnerabilities | RA-5, SI-2 | High | 0-3 months | Phase 1: Quick Wins | 25000 | IT Manager | Not Started | Reduce attack surface from known vulnerabilities
REC-005 | R-012 | Implement Centralized Logging | Deploy centralized logging solution, onboard critical systems, establish log retention policy | AU-2, AU-3, AU-12 | High | 0-3 months | Phase 1: Quick Wins | 50000 | IT Manager | Not Started | Foundation for monitoring and forensics
REC-006 | R-003 | Deploy SIEM and Security Monitoring | Implement SIEM solution (e.g., Microsoft Sentinel), onboard critical systems, create detection use cases | SI-4, AU-6, IR-5 | Critical | 3-6 months | Phase 2: Detection & Response | 200000 | IT Manager | Not Started | Visibility into security events and threat detection
REC-007 | R-008 | Develop and Implement Incident Response Plan | Create comprehensive IR plan, establish IR team, develop runbooks, conduct tabletop exercises | IR-1, IR-4, IR-8 | Critical | 3-6 months | Phase 2: Detection & Response | 75000 | CISO / IT Manager | Not Started | Effective incident handling and containment
REC-008 | R-006 | Enhance Remote Access Security | Implement MFA for VPN (if not in Phase 1), establish contractor access management, deploy network access control | AC-17, IA-2(1), AC-20 | High | 3-6 months | Phase 2: Detection & Response | 80000 | Network Team Leader | Not Started | Secure remote access controls
REC-009 | R-011 | Enhance Security Awareness Training | Implement phishing simulation platform, create role-based training, establish quarterly awareness campaigns | AT-2, AT-3 | Medium | 3-6 months | Phase 2: Detection & Response | 40000 | HR Manager / CISO | Not Started | Reduce human error and improve security culture
REC-010 | R-012 | Implement Log Review and Monitoring Procedures | Establish log review schedules, create monitoring dashboards, define alerting thresholds | AU-6 | High | 3-6 months | Phase 2: Detection & Response | 30000 | IT Manager | Not Started | Proactive threat detection and compliance
REC-011 | R-002 | Implement Data Classification and Governance Program | Conduct data discovery, implement classification scheme, label data, establish data governance policies | SI-12, MP-3 | Critical | 6-9 months | Phase 3: Data Protection | 120000 | Data Protection Officer | Not Started | Foundation for data protection and compliance
REC-012 | R-002 | Deploy Data Loss Prevention (DLP) Solution | Implement DLP for O365, email, and endpoints, configure policies based on data classification | SC-28, MP-6 | Critical | 6-9 months | Phase 3: Data Protection | 150000 | IT Manager | Not Started | Prevent unauthorized data exfiltration
REC-013 | R-005 | Establish Third-Party Risk Management Program | Create TPRM framework, develop vendor assessment questionnaires, update contracts with security clauses | SR-1, SR-2, SR-3 | High | 6-9 months | Phase 3: Data Protection | 60000 | Procurement Manager | Not Started | Manage supply chain security risks
REC-014 | R-010 | Implement Change Management Process | Develop change management procedures, implement approval workflows, establish change advisory board | CM-3, CM-6 | Medium | 6-9 months | Phase 3: Data Protection | 40000 | IT Manager | Not Started | Control configuration changes and reduce risk
REC-015 | R-009 | Implement Removable Media Controls | Develop removable media policy, restrict USB usage, implement USB monitoring and DLP for removable media | MP-1, MP-7 | Medium | 6-9 months | Phase 3: Data Protection | 35000 | IT Manager | Not Started | Prevent data exfiltration via removable media
REC-016 | R-004 | Establish Cyber Risk Assessment Program | Develop risk assessment methodology, conduct organization-wide cyber risk assessment, establish annual cadence | RA-1, RA-3 | High | 9-12 months | Phase 4: Continuous Improvement | 80000 | CISO / Risk Manager | Not Started | Risk-based decision making and resource allocation
REC-017 | R-010 | Extend Asset Inventory to Complete CMDB | Inventory all software, SaaS applications, cloud resources, and third-party vendors in CMDB | CM-8 | Medium | 9-12 months | Phase 4: Continuous Improvement | 50000 | IT Manager | Not Started | Complete visibility into organizational assets
REC-018 | R-002 | Implement Encryption Key Management | Develop encryption policy, implement key management procedures, document encryption usage | SC-12, SC-13 | Medium | 9-12 months | Phase 4: Continuous Improvement | 60000 | IT Manager | Not Started | Proper cryptographic controls and key lifecycle
REC-019 | R-003 | Establish SOC or MSSP Partnership | Evaluate build vs. buy for SOC, establish 24/7 monitoring capability, hire or partner for security operations | SI-4, IR-5, AU-6 | High | 9-12 months | Phase 4: Continuous Improvement | 250000 | CISO / IT Manager | Not Started | 24/7 threat detection and incident response
REC-020 | R-008 | Conduct Cyber Crisis Simulation Exercise | Plan and execute full-scale cyber crisis simulation, test IR plan, engage executive leadership | IR-3, CP-4 | Medium | 9-12 months | Phase 4: Continuous Improvement | 45000 | CISO | Not Started | Validate readiness and improve response capability

## Executive Summary
OSCORP INDUSTRIES - CYBERSECURITY ROADMAP
Implementation Timeline: 12 Months
Phase | Timeline | Focus Areas
Phase 1: Quick Wins | 0-3 Months | MFA, PAM, Policies, Vulnerability Management, Centralized Logging
Phase 2: Detection & Response | 3-6 Months | SIEM, Incident Response, Enhanced Monitoring, Awareness Training
Phase 3: Data Protection | 6-9 Months | Data Classification, DLP, TPRM, Change Management
Phase 4: Continuous Improvement | 9-12 Months | Risk Assessment, SOC/MSSP, Advanced Controls, Crisis Simulation
Investment Summary
Phase 1 Total | $300,000 | Critical foundation and quick wins
Phase 2 Total | $425,000 | Detection and response capabilities
Phase 3 Total | $405,000 | Data protection and governance
Phase 4 Total | $485,000 | Continuous improvement and maturity
TOTAL INVESTMENT | $1,615,000 | Complete cybersecurity transformation
Key Outcomes
• Reduced risk of data breach by 70%
• Improved incident response capability from 0% to 90%
• Achieved NIST CSF maturity from 28% to 75%+
• Established 24/7 security monitoring
• Comprehensive data protection and governance
• Third-party risk management program
• Board-level cybersecurity visibility and reporting