## Policy Mapping
NIST Control ID | Required Policy | Policy Status | Priority | Policy Scope / Key Requirements | Target Timeline | Policy Owner
IA-2, IA-2(1) | Authentication and Multi-Factor Authentication Policy | Missing | Critical | Define authentication requirements, MFA implementation, password standards | Month 1 | CISO / IT Manager
AC-1, AC-2 | Access Control Policy | Missing | Critical | Define access control principles, RBAC model, access request/approval process | Month 1 | CISO / IT Manager
PL-1, PL-2 | Information Security Policy | Weak | Critical | Comprehensive information security policy covering all security domains | Month 1-2 | CISO / IT Manager
IR-1, IR-4, IR-8 | Incident Response Policy and Plan | Missing | Critical | Define IR procedures, roles, escalation, notification, containment, eradication | Month 2 | CISO / IT Manager
AU-1, AU-2, AU-6 | Logging and Monitoring Policy | Missing | Critical | Define logging requirements, retention, review procedures, SIEM requirements | Month 2 | CISO / IT Manager
SC-12, SC-13, SC-28 | Data Protection and Encryption Policy | Missing | High | Define encryption requirements, key management, data at rest/in transit protection | Month 2 | CISO / IT Manager
SI-12, MP-3, MP-6 | Data Classification and Handling Policy | Missing | High | Define data classification scheme, handling requirements, disposal procedures | Month 2-3 | CISO / Data Protection Officer
SR-1, SR-2, SR-3 | Third-Party Risk Management Policy | Missing | High | Define vendor assessment process, security requirements, contract clauses | Month 3 | CISO / Procurement Manager
RA-1, RA-3 | Cyber Risk Assessment Policy | Missing | High | Define risk assessment methodology, frequency, documentation, treatment | Month 2 | CISO / Risk Manager
RA-5, SI-2 | Vulnerability Management Policy | Missing | High | Define scanning frequency, remediation SLAs, patch management procedures | Month 2 | CISO / IT Manager
CM-1, CM-3 | Change Management Policy | Missing | Medium | Define change approval process, testing requirements, documentation | Month 3 | IT Manager
MP-1, MP-6 | Removable Media and USB Policy | Missing | Medium | Define USB restrictions, removable media controls, data transfer procedures | Month 3 | CISO / IT Manager
AT-1, AT-2, AT-3 | Security Awareness and Training Policy | Partial | Medium | Enhance existing training with role-based training, frequency, phishing simulations | Month 2 | CISO / HR Manager
AC-17 | Remote Access Policy | Missing | Medium | Define VPN requirements, MFA for remote access, contractor access controls | Month 2 | IT Manager / Network Team
CM-2, CM-6 | System Configuration and Hardening Policy | Partial | Medium | Extend SOE baselines to all systems, define hardening standards | Month 3-4 | IT Manager
PE-1, PE-2, PE-3, PE-6 | Physical Security Policy | Implemented | N/A | Physical security policy exists and is well-enforced | Ongoing | Security Manager
CP-1, CP-2, CP-9 | Business Continuity and Disaster Recovery Policy | Implemented | N/A | BC/DR policy exists, plans tested regularly | Ongoing | IT Manager